## Sheet1
Smartsheet
DueDate
Use Cases | 2019-09-05
Use case analysis and environment study, platforms research, Widgets, ScreenPop, Agent/Admin Portals, UCM, Jabber, anyConnect, VPN, xml
2019-10-18 | To Do
B&S and Finesse
scripts for automation current?
Parallel time line B&S Finesse with Rhonda
Phase one dialer testing and logging using B&S, Salesforce integration
Tech input parallel and requirement signed off, with Molina, Daily meetings with Molina in regards to telephony, Salesforce and Finesse specifically
Mike, Sravan and Victor, Qntx same page, Telephony, Screenpop parallel reqs and routing reqs parallel using same data.
TechDesign | 2019-10-27
automation testing analysis to George, Rhonda, Alex and Greg from Victor, Sravan, and Mike respective to each role
Logging correct variable to Salesforce. Click toCall Click to update click to send click for ready/not ready status working
telephony 2nd test live first time using live agents, B&S and salesforce
Screen pop gadgets signoff
outlook outgoing marketing cloud with sms/text option research for decision makers 2020 campaign outline/diagram/research maybe out of scope
Telephony | 2019-11-18
Telephony api config final testing
AppLive1.0 | 2019-11-30 | launch party